## Sheet1 (hidden)
Next Steps Matrix
| Client |  | Last Updated - | 2025-09-12 |  | Complete
| Contact |  | Targeted Start Date | 2025-09-17 |  | In-Progress
Deleted
Column 1 | Column2 | Where to Find | Assigned To | Notes | Completion Date | Status
IC Team
| Meets IC Team Goals | Recordings/Proposals |  | Recording/Proposals
| Questions/Answers |  |  | Features/Roadmap/Integrations
IT/Security
| SOC 2 T2 |  | Client
| Vendor Risk |  | Client/Cerkl
IT/Security focused Q/A meeting
NDA's
Procurment
| Pricing agrred upon | Proposal
MSA - Cerkl's or Clients
Timeline
| Approvals |  |  | IT/Finance/Vendor Management
| Signatures | Docusign

## Project Plan
Webinar Date: |  | 2026-04-30 | Webinar Brief: |  | Matt Frost Webinar Brief
Collaboration Partner: |  | Matt Frost
Category | Type | Task | Priority | Owner | Status | Due Date | Deliverable | Notes
Planning Phase | Meeting | Review Mutual Action Plan | P0 | Cerkl | Completed | 2026-03-20
Planning Phase | Meeting | Agree on weekly meeting date/time | P0 | Joint | Completed | 2026-03-20 |  | Wednesdays, 8am ET
Planning Phase | Meeting | Finalize webinar topic and objectives | P1 | Joint | Completed | 2026-04-02 |  | Matt Frost Webinar Brief
Planning Phase | Meeting | Confirm date, time and platform for the event | P1 | Joint | Completed | 2026-03-19 |  | Thu, Apr 30, 2026
Planning Phase | Meeting | Agree on giveaway | P2 | Matt Frost | Completed | 2026-04-13
Content Development | Task | Collaborate on a webinar outline, script and visuals | P1 | Joint | In progress | 2026-04-27
Content Development | Task | Provide short bio, headshot for registration page, social media and promotional materials | P1 | Matt Frost | Completed | 2026-04-08
Content Development | Task | Create tracking URLs | P2 | Cerkl | Completed | 2026-04-14
Promotion | Task | Launch registration page | P0 | Cerkl | Completed | 2026-04-09 |  | Generic, untracked page draft
Promotion | Task | Creation of email and social media campaigns | P3 | Joint | Completed | 2026-04-09
Promotion | LinkedIn | LinkedIn Post: Introduce the webinar, highlight its value, provide a registration link. Link to blog post. Tag Speaker. | P2 | Cerkl | Completed | 2026-04-16
Promotion | Email | Email Blast: Introduce the webinar, highlight its value, provide a registration link. Include both logos. | P1 | Matt Frost | In progress | 2026-04-21
Promotion | Email | Email Blast: Introduce the webinar, highlight its value, provide a registration link. Include both logos. | P1 | Cerkl | In progress | 2026-04-21
Promotion | LinkedIn | Write and publish Thought Leadership post | P0 | Matt Frost | In progress | 2026-04-21
Promotion | LinkedIn | LinkedIn Post: Introduce the webinar, highlight its value, provide a registration link. Link to blog post. Tag Cerkl. | P2 | Matt Frost | Not started | 2026-04-20
Promotion | Blog | Write and publish the first blog post introducing the topic and speakers. Link to speaker website. | P0 | Cerkl | In progress | 2026-04-21
Promotion | Email | Email #2 reiterating key points and benefits. | P2 | Matt Frost | Not started | 2026-04-27
Promotion | Email | Email #2 reiterating key points and benefits. | P2 | Cerkl | Not started | 2026-04-27
Promotion | LinkedIn | Boost last-minute registrations, reiterating key points and benefits. | P1 | Cerkl | Not started | 2026-04-28
Promotion | LinkedIn | Boost last-minute registrations, reiterating key points and benefits. | P2 | Matt Frost | Not started | 2026-04-28
Promotion | Email | Email #3 - last minute reminder, reiterating key points and benefits. | P2 | Matt Frost | Not started | 2026-04-29
Promotion | Email | Email #3 - last minute reminder, reiterating key points and benefits. | P2 | Cerkl | Not started | 2026-04-29
Webinar | Rehearsal |  |  |  |  | 2026-04-27 |  | 3pm (10am EDT)
Webinar | Event | Host the live event with a recording | P0 | Cerkl | Not started | 2026-04-30
Follow-up | Email | Distribute the recording and asset to all registrants | P0 | Cerkl | Not started | 2026-05-01
Follow-up | Task | Share registrations with speaker(s) | P0 | Cerkl | Not started | 2026-05-01
Follow-up | Task | Release a post-webinar blog with a summary and key takeaways | P0 | Matt Frost | Not started | 2026-05-05
Follow-up | Task | Select and notify giveaway winner | P0 | Matt Frost | Not started | 2026-05-05

## Registration Links
cerkl_linkedin | https://us02web.zoom.us/webinar/register/2617762528258/WN_6CQcs14XRJeKF567KBWK7Q
cerkl_email | https://us02web.zoom.us/webinar/register/2317762528324/WN_6CQcs14XRJeKF567KBWK7Q
matt-frost_linkedin | https://us02web.zoom.us/webinar/register/3617762528426/WN_6CQcs14XRJeKF567KBWK7Q
cerkl_customer-success | https://us02web.zoom.us/webinar/register/5417762528644/WN_6CQcs14XRJeKF567KBWK7Q
cerkl_cerklular | https://us02web.zoom.us/webinar/register/4317762528802/WN_6CQcs14XRJeKF567KBWK7Q
cerkl_icpro | https://us02web.zoom.us/webinar/register/7917762528892/WN_6CQcs14XRJeKF567KBWK7Q
matt-frost_email | https://us02web.zoom.us/webinar/register/9817762529325/WN_6CQcs14XRJeKF567KBWK7Q
cerkl_sales | https://us02web.zoom.us/webinar/register/4517762529666/WN_6CQcs14XRJeKF567KBWK7Q
cerkl_innercerkl-news | https://us02web.zoom.us/webinar/register/7717762543467/WN_6CQcs14XRJeKF567KBWK7Q
matt-frost_website